## V12
1. What did you intend? (20%) ▼ What were your objectives? Why did you take this action? What were you trying to achieve? ▼ What were the key assignments? | What happened? (<10%) ▼ Get multiple perspectives: There is no single best story about what happened. ▼ Focus on "facts" (e.g., costs, number of people involved, figures, etc.) and “opinions” (e.g., what worked and why, what happened). ▼ No blaming: Focus on events and what events preceded or followed, not why someone did something or what you thought about it. ▼ Allow very specific comments as well as abstract and conceptual ones | 4. What should we do next time? (40%) ▼ What worked that may not work again? What worked that you want to repeat? What do you want to do differently? ▼ Spend ~50% of the discussion here to keep from falling into bad habits and failing to start good new ones. | What should we do now? (<10%) ▼ How will you share these lessons? ▼ Don’t just wait until next time if you can make a difference now. ▼ Be clear about assignments and responsibilities: who will do what by when?
•All actionable feedback documented and prioritized for implementation quickly. | •Acquisitions caused major re-plans of projects after development had started | •Acquisitions need to be part of the following PI planning & roadmap | •About box updates need to be included in the products by Feature Freeze at the latest; any changes past feature freeze must be CCBed and re-verified
•Alpha/Betas start on time according to initial plans. | •Acquisitions were not tracked to the same level as existing products | •AI Success Teams concept was a valuable way to promote visibility into customer feedback and engage cross functional groups early in product development, to get ready for release. | •Align all teams on the same program increment planning and execution schedule
•Approval by Executives to go to RTM | •Acquisitions were not tracked to the same standards as the rest of the portfolio, which caused issues when dependencies were needed to be delivered | •Any acquisitions need to be integrated into our systems right away, should not allow for them to exist independently of the rest of the products | •Aligning all teams (agile & non-agile) on quarterly program increment planning
•At the end of each phase, teams were expected to reach Feature Freeze quality criteria for the scope committed to | •Actionable beta feedback documented quickly for key projects that had AI success teams, but not as much for other teams. | •Back-office cannot support the development of two releases concurrently | •All dependencies must be identified as part of PI planning and agreed to with all impacted teams (producers and consumers). Must be tracked and reviewed weekly
•Automated tracking of strategy, inception, and elaboration deliverables | •Agile and non-agile teams had different dashboards/tracking | •Better outlook for alpha/beta plans is required so emergencies occur much less often. | •All teams will be on the same program increment cadence starting Nov ’20
•Beta plans identified for each construction phase for each product, with the expectation that teams would front-load beta targeted features early in development so an extensive beta could be held and feedback incorporated into V12 early. | •Alpha/Betas for several 1.0 innovations started significantly later than planned hence causing 2-month GA delay. End to end workflows not fully tested prior to declaring beta readiness. | •Build spec must be validated and distributed amongst all teams, and all changes must be approved and acknowledged by all impacted teams | •Automate translation project creation & export
•Betas identified in elaboration/PI planning kicked off at the end of each phase | •Automated reporting for AI Success Beta Programs tracking beta metrics and team progress against goals | •Change at the use case level does not require change management and should be managed by the team | •Business planning should be a periodic activity, not a singular event for a release
•Change management done through CCB process for all scope changes or exceptions, with Executive approval required for MVP level changes | •Change management was not applied consistently across agile vs. non-agile teams, and almost none in APM | •Customers lose momentum in beta testing without continuous engagement & check ins by AspenTech. It is difficult to expect most customers to be self-motivated. | •Continue AI Success Team concept post V12
•Consistent, automated tracking of product turnovers, defects, test metrics through Power BI Reports for all Product teams | •Continuous customer engagement was not continuous for most areas except AI Model Builder. Too many silos in some cases limited exposure across customer organizations. | •Customers respond very positively to continuous Innovation Club engagement, as well as 1:1 attention from AspenTech. | •Dependencies will be reviewed weekly
•Continuous engagement with customers to promote excitement & build adoption pipeline. | •COVID-19 impacted schedule of some vendors | •Defining all features up front is not a good use of time as features are likely to change/evolve over the release | •Develop mechanism for all product teams to review beta feedback regularly as part of regular team processes which will also increase overall visibility. Also ensure bandwidth for implementing customer feedback into same release.
•Deliver V12 release in August with all requirements finalized and approved 3 months prior to GA date for back-office teams | •Customer beta validation feedback was lower, and later, than expected compared to sign up interest. | •Dependencies must be explicitly identified and agreed to by the producer and consumer | •Devote more resources (time) to AspenTech’s customer interactions during beta, to ensure customers are prioritizing our beta activities & sharing key feedback early.
•Execute the innovation projects using agile methodology | •Decision made to have two V12 releases in order to meet business needs | •Dependencies must be identified and agreed to by all impacted teams at the same time | •During PI planning, teams must identify their integrations and end-to-end workflows, with the expectation to hold a demo of this at the end of the PI with all stakeholders
•Final USB media created from gold media, final verification completed resulting in RTM | •Delays in infrastructure being made available to support customer beta volume, which had some impact on start dates. | •Dependencies need to be tracked in our ALM tools effectively | •Eliminate all manual edits to resource files/translated files that R&D provides/PMO updates after translations
•Following RC declaration, final medias built and verified, resulting in gold media declaration | •Dependencies across teams were not well planned and managed, leading to delays in deliverables | •Dependency tracking is necessary and was not done sufficiently for V12 | •Going forward, ensure sufficient internal end to end workflow testing & validation with customer models prior to betas of brand-new workflows.
•Pricing & licensing was supposed to be approved by June ’19 | •Dependencies were not adequately identified and committed to | •End-to-end workflows need to be identified, integrated, and tested earlier in the process | •Hire PMO owner for localization
•Product Managers were expected to define the full set of features for V12 in a single inception phase, targeted for 11/5/18 | •Did not reconcile what approval to go to RTM means for SaaS teams, hence SaaS teams were not ready to seek approval when RTM was required | •Features should be sized appropriately to be completed in a phase | •Hold continues reviews for media and software delivery spec for early alignment
•Products are expected to stop all changes at code freeze to allow QE to complete final verification leading up to RC | •Experienced delays in both translations and validations for some languages. Had to merge some activities to accommodate new schedules | •Having agile & non-agile teams planning and developing on different schedules is not good, difficult to keep teams aligned and work dependencies | •Hold system demos every quarter for major projects/integrated workflows
•Robust & sufficient customer beta validation, particularly for key projects, with good feedback to sign ups ratio. | •Help/About Box updates were accepted not in the media, which is not the process | •Having three elaboration/construction phases of different lengths was confusing | •Identify all dependencies and commitments to them in each planning session
•Teams were expected to achieve milestones without delays to deliver planned scope for each phase | •Inception completed 12/14/18, which did not include any of the Innovation projects | •If a major release with dependencies is split into multiple delivery dates, common components must be evaluated on an individual basis to determine where changes can/cannot/must occur | •Identify integration points per quarter
•Teams were expected to define their product roadmap looking out 18 months through the release of V12 | •Incremental planning occurred for both agile & non-agile teams | •Impact from new agile initiatives to RUP projects were not clearly identified | •If any acquisitions happen, migrate them to the existing ALM tools and reporting structure as early as possible, do not allow for long-term exceptions
•Teams were to deliver all planned translations at V12 GA with all translations & validations executed according to the schedule. | •Innovation project inception completed 3/19/19, which is after the teams held their first PI Planning | •Integration milestones must be identified | •Integrated workflows need to be fully defined and owned, including testing
•Three separate elaborations were to be held at pre-defined dates throughout the V12 release cycle | •Innovation project scope was committed to after the rest of V12 scope, significantly impacting original plans | •Iterative planning is beneficial, but needs better synchronization | •Integration testing needs should be identified each quarter
•V12 originally targeted to deliver in August ‘20 | •Late approval of multi-case pricing/licensing caused major issues and delays in ENG | •Major changes to the roadmap caused major re-plans when plans are defined for long timeframes | •Investigate options for eliminating the manual update & verification needs for the product manifest, to enable manifest validation to occur periodically, not just after RC
| •Late requirements for end-to-end integration testing were identified and made getting to beta very difficult for some products | •Media and software delivery specs should be developed and reviewed periodically | •Limit the size of a feature to be able to be completed in a single quarter
| •Lost the key resource program managing the localization efforts for all areas | •More early testing of full end to end workflows should have been required well before beta start to ensure beta readiness & start on time. | •Maintain a prioritized feature backlog that is continuously reviewed and updated
| •Lost the key resource program managing the Product Delivery Team | •Need scalable solution post V12 for ensuring all beta feedback is quickly reviewed & prioritized by all product teams. | •Major dependencies must be clearly identified during planning
| •Major projects/workflows did not work together until we were approaching beta | •Need to move ALL products to supported file formats that don’t require manual edits | •Media & software delivery spec should be owned by the same person
| •Many betas were pushed to later in cycle, and several last-minute beta requests. | •On a quarterly basis, teams need to come together and demonstrate progress | •Provide a consistent, streamlined CCB process that is understood and adhered to by all
| •October release testing cycle coincided with end-of-quarter activities | •Planning & Execution each needs to occur at the same time across the portfolio | •Provide updated template (or new methodology) for pricing/naming/licensing proposals that will answer standard set of questions for different back office systems
| •Planned scope was larger than estimated which resulted in MVP scope changes | •Portfolio alignment is required, teams can’t plan in silos | •Reduce Innovation Club silos post V12 and ensure engagement is ongoing and consistent to better promote overall customer engagement and adoption pipeline.
| •Pricing and licensing proposals and approvals came very late in the cycle (up to May ‘20 for final approvals), making it difficult for R&D to implement the work on the original schedule | •Pricing & Licensing changes must be considered earlier in the release cycle and tracked as part of the backlog like all other work | •Require at the exit of PI planning – concrete alpha/beta plans for upcoming PI (3-month outlook), and tentative plans for following PI (6-month outlook).
| •Pricing, licensing and naming changes not defined/approved until late in the cycle which made it difficult for back office teams to implement and test work | •Pricing, licensing and naming proposals should include basic information needed for back office systems | •Require PM to get approval for pricing/licensing changes at least one PI prior to when the work is expected to be implemented (also avoiding licensing changes in the final PI of a release when possible)
| •Products not built with correct versions of common components | •Pricing, naming and licensing requirements need to be defined and approved at least 3 months prior to release date in order to allow sufficient time for implementation and testing | •Require PM to get approval for pricing/licensing changes at least three months prior to release
| •Program increment planning for agile teams was not held on a consistent cadence across teams; APM was not synchronized with the rest of the Agile products | •Product manifest verification should be built into the process, not done once at the end when change is expensive | •Review and align on roadmap prioritizations quarterly across the portfolio
| •Several product teams had CCBs after code freeze for defects discovered late | •Strategy needs to be revisited throughout a release cycle to ensure it is still aligned with business & market needs | •Roadmap needs to be evaluated regularly for changes
| •Significant delays to major milestones for many areas | •There are areas that can be automated to speed up the process | •Teams should develop features for a shorter time horizon
| •Team had limited time to develop the October release, and lots of questions raised around implementation details | •This will allow more resources to help with the project | •Train teams on how to set dependencies and use the dependency tracker in VSTS, include the dependency tracker as part of team dashboards and review in the weekly solution release train meetings
| •Teams scrambled at times going into PI planning due to backlogs not being sufficiently prepped | •Visibility into AI success beta programs was helpful and higher engagement from the team and faster actions when needed | •Update the back office systems incrementally for approved changes (need to be able to support concurrent releases)
| •The PI Planning had an impact on the elaborations for RUP teams which lead to them not being aligned with agile teams when planning | •Visibility into product backlog status is critical for ensuring successful program increment planning | •Use consistent dashboards and metrics wherever possible across agile and non-agile teams
| •The three elaboration phases occurred, but there was also additional/extended elaborations held for acquisitions | •When scope fell out of a phase, teams did not do a good job of re-assessing what was possible for the overall release
| •Two acquisitions occurred 1 year later (July ’19), resulting in re-plan of several V12 projects | •When we seek approval for RTM, we need to have new SaaS products in a state that is ready for approval as well
| •Unified delivered on the original V12 schedule, the rest of V12 delivered 2 months later | •Will shorten execution time which is currently time consuming and error-prone
•Visibility into dependencies across teams was not sufficient
•When V12 was delayed, decision made to hold Unified to original GA while the rest of the products moved 2 months, causing a complex delivery scheme

## V14.X
1. What did you intend? (20%) ▼ What were your objectives? Why did you take this action? What were you trying to achieve? ▼ What were the key assignments? | What happened? (<10%) ▼ Get multiple perspectives: There is no single best story about what happened. ▼ Focus on "facts" (e.g., costs, number of people involved, figures, etc.) and “opinions” (e.g., what worked and why, what happened). ▼ No blaming: Focus on events and what events preceded or followed, not why someone did something or what you thought about it. ▼ Allow very specific comments as well as abstract and conceptual ones | 4. What should we do next time? (40%) ▼ What worked that may not work again? What worked that you want to repeat? What do you want to do differently? ▼ Spend ~50% of the discussion here to keep from falling into bad habits and failing to start good new ones. | What should we do now? (<10%) ▼ How will you share these lessons? ▼ Don’t just wait until next time if you can make a difference now. ▼ Be clear about assignments and responsibilities: who will do what by when?
[yawad] Assess to what extent the customer can be self-sufficient | 1.) Build a patch, validate the patch, posting of the patch on CS&T. This entire process was not smooth for the release. The team went through 5-6 iterations to post the patch. Combination of Patch to have Full Install and partial install on the support site, lot of unknowns, zip file was corrupted. | [Lisa] Defect fixing in an earlier schedule, to allow detecting the additional issues involved by defect fixing through regression testing. | Add task to PDT Plan for updating media inventory in Oracle (Jamie)
[yawad] Understand customer's constraints. e.g. security policies | - Network issues were addressed. File size was big. | [Lisa] Not APC: UPL to have good plan, not delay product milestones. | Add the user's name to the app bar (blue bar) to make it clear to the user which account they are logged in to. Consider implementing a similar solution for all web-based tools to help users know that they are logged in and which account they are using.
[yawad] Validate installation procedure of Aspen Cloud 2.0 | [Doc (John R.)] The detailed test cases created by QE were incredibly helpful in drafting the V14.2 APC documentation. | [yawad] Developers waited for meetings to be setup. Direct engagement for technical issues. | Continue the reviews and re-work that results until the products meet Aspen Quality Requirements
[yawad] Validate that AIMB can be used in a private cloud | [K.C.] Deferred Defect 933113: Failed to export the full .CLC file for large dataset and DMC3 Builder crashed to declare code freeze. The root cause of the issue is when there is not an unfragmented block of memory to allocate the clc file to. The change to 64-bit caused this issue because of the increase in size of certain data types. The way to resolve this would be to allocate memory piece by piece rather than all at once. | [yawad] Less attendees during the working session | Create a contact list of all the PDT team members to show what they all do, who is responsible for what areas, do we have the correct stakeholders, etc (updated with new team members when they join)
[Yawad] We planned to have customers log in to the E support site to download the credentials to download the Docker container and installer (on similar lines to how Maestro is getting delivered) | [K.C.] Deferred Defect 952932: V14.2 DMC3 Builder ¦ Crash when clicking the Save button in the Import IP21 Data dialog without tag list existing. QE found a crash defect after code freez when a user clicks Import button in Import IP21 Data dialog without specifying the Data Source first and ignoring the warning message. The correct behavior should be that the Import button is disabled if Data Source field is empty or a warning message is issued. The project file can be fully recovered after the crash when the user reopens DMC3 Builder. We plan to fix it in a V14.2 patch. | [yawad] Quicker turnaround on our end, if possible | DG: SaaS (in some form, potentially provided by a 3rd party) must continue for the foreseeable future as our customers' cloud strategies develop.
· Defect back log remains under 121 (APEM)/12 (AORA/ATOMS) | [K.C.] Regression testing identified missing Web.21 AtPersistence.asp file that APC depends on. Dataworks removed both Process Explorer and Web.21 AtPersistence files since they were no longer used by them, and the Process Explorer version of the file was identified as a security vulnerability by a customer. The Web.21 AtPersistence.asp file was not added back to V14.2 and underwent security improvements and scanning and will be added back for APC in a future patch. | · AORA/ATOMS | EP (<5 fixes) vs Feature Pack (Enhancements) discussion.
· Release V14 in Nov 2022 successfully. | [K.C.] We had 116 defects open at code freeze vs 100 defect limit. We worked on creating V15 media and implementing v15 use cases in parallel to the v14.2 release and majority of the surge in defect number are related to this. | · APEM | Need a master list of approvers, what they need to approve, etc
· Achieve Code freeze on September 26th meeting quality criteria and with no CCB. | [Lisa] Use Cases are delivered to QE on time in v14.2. And there are clear/detailed turnover recordings or documents for QE testing. | · ARF (Defect 803389) | Need to rollout betas for different products different times.
· Achieve final Feature Freeze on Aug 15th meeting quality criteria and with no CCB. | [LO]Customer thought that system was very stable and did not see any failures. Some of the issues were of the install nature. Those Install issures were resolved very quickly | · At least 80% of the scope to be planned and create a CCB. Planning needs to be socialized earlier and add it to the Aha Backlog. | PI16 and PI17 should have focus on MVP features. Note: Not adequate time to plan for MVP features in PI16 due to V14 release timeline.
· Achieve final Scope Complete on July 5th meeting quality criteria and with no CCB. | [LO]Testing in Southeast Asia helped a lot | · Have the dedicated PM and communication on the upcoming services to be addressed early. | QE team could use the rest API and do 90% of the job
· Achieve GA (general availability) on November 14th meeting quality criteria and no CCB | [Raju] We faced challenges getting existing code because it was not managed by IS, despite having a similar product called container delivery by APM BU | · Streamline the communication with services and PMs, sequence of events. | Raven to present QE leadership with business case to support hiring of more QE resources for upcoming releases
· Achieve Release Candidate on Nov 4th meeting quality criteria and with 1 CCB. | [yawad] Customer was very prepared | 1.) Any Security improvements/initiatives consume resources. Propose to plan security initiatives upfront, so the tasks are completed on time. Aspen Security team needs to be aware of the planned scope change for any new request. For example: 140 security items were added late to Aha! during V14 release. | Review PDT spreadsheets and see how we can improve (i.e utilizing smartsheets, sharepoint, etc)
1.) Release AU V14 CP2 [AURA, AUP, AUS, SPSP and AU GDOT Builder] | [yawad] Deployment of AIMB in private cloud was succesful | 1.) Continue to allocate time in each PI for Defect fixing. | SCs cross train and seek out for help when needed. We don’t want big customers and partners to lose confidence in our product due to lack of knowledge of our products.
1.) Release V14 APC | [yawad] Installation procedure was validated and aligned with customer's security policies | 1.) Find out the CS&T person in charge of the posting have a proper documentation process. | Stay disciplined
1.) Release V14 GDOT. | [yawad] It spanned a few months instead of days | 2.) CS&T would not known about posting the KB article and made available on the update center. | We may need to obtain the source code and make modifications, as it was designed for containers. We will need to review the code and identify the necessary changes. The source code is currently managed under our control. We plan to modify this function, as it is currently only working for the APM product. We want to understand how it works and make it more general-purpose.
1.) Release V14.2 APC | [yawad] Some security constraints required escalation from Customers to get access | 2.) Prioritize the features MVP/non-MVP within a release. PMs should also have non-MVP features, for flexibility when resources are constrained.
2.) Complete committed Use Cases in PIs | [yawad] The installation was able to work around security constraints without making the procedure bespoke for Chevron | 2.) Several customer escalations in the V14 development cycle were for non-software issues, attributed to application configuration, and complexity required for Services team implementation. Learnings to be incorporated in V14x and future releases for alignment with simplification initiatives, focused on software ease-of-use and related tools and features to assist in application design, configuration, and commissioning.
2.) Complete committed Use Cases in PIs | [yawad] Too many people from AspenTech during the working sessions | 3.) Data science team members should have base knowledge of the product, to make significant contributions for feature execution within a release.
2.) Complete committed Use Cases in PIs | [yawad] Two type of issues: 1) a couple of bugs, normal since it was the first time, 2) cusomter security constraints. | 3.) Set it as Default in the process. CPs to be posted on update center and support site.
2.) Complete committed Use Cases in PIs. | [Yward] we have not yet set up the feedback collection process, but we discussed it with Monica last week and agreed that we should do so. [Devin] we received feedback from the AIMB user, Susan, and her feedback was straightforward and expected from the user's point of view. She said that Azure Active Directory worked well. Susan was able to log in to AIMB without having to sign in, which was confusing for her. She was also confused about where or how her work would be saved | 4.) Documentation gaps to be looked at by the team to improve communications. Action item: initiate review of draft documents earlier in the development cycle.
3.) GDOT development team was able to meet all quality criteria milestones, with open defects below the backlog limit before the release. | § APM team used the Internal tool for localization for PI13 and PI15 and shared good feedbacks | 4.) EPs to be not posted on the update center.
A lot of the defects in localization | §Customer centric - agile planning/prioritization | 5.) Best practice is when working from home, RDP rather than VPN.
Achieve good product quality | §Defect processing – Pending Verification limits by PI (self imposed) | 5.) Continue to have more early engagements with customer feedback for example: Alpha/Beta to incorporate customer feedback and add it to the current release.
APC development team was able to meet all quality criteria milestones, with open defects below the backlog limit before the release. | §distribute the testing load through each PI. | 6.) PM and CS&T customer engagement programs have resulted in low Escalations from customers.
APEM V14 CP1 for Sep’23 GA. Milestones (SC- 7/14 7/21, FF- 8/11, CF- 9/8, RC – 9/15, GA – 9/22) | §Good communication for integration features (Expo, Mtell etc..) | 7.) Security Scans defects were found towards the end of release. Only critical and high-risk defects were fixed by Development, but some customers requested that medium security defects also be addressed. Recommendation from the team while planning to fix only the critical and high defects, is to also look at the medium defects. Action Item: Dev team to follow up with Product Security team.
Back office training held for all back office staff | §Improve accuracy of the estimates | 8.) More internal Transparency of Security scan reports to PM was requested. Action Item: Dev team to follow up with PM and share the reports for visibility.
Beta testing to start at the FF stage | §Improve the team and vendor coordination. | 9.) Escrow procedure should have been in place by the time we hit RC. Then we could have performed the escrow as part of the immediate follow-on work for RC. Request was sent to the teams after GA, where teams were fully into work on V15 and are expected to find a bunch of time for escrow. This is an unnecessary and foreseeable interruption in V15 work.
CCB815192 Quality Exception (Defects) for V14 - Platform support issue about new feature | §Individuals thinking outside of the box, “wearing user/multiple hats” – focus on value added workflows | a. Recent process was changed in CS&T. Talk to Andrew and Venu tp help in this area where the CP should be made available on the update center.
Clean, clear & specific file(s) to load into the system | §Move to Program Increment based development | Ability to spun up a machine with Graphic Card for Optiplant. Note: Budget/Cost to be monitored carefully.
Configure salesforce/oracle to deliver new V14 media | §Product teams appreciated the PI approach introduced for V14 release. | Action Item: Provide guidance on the CCB proposal on high level flow. Update the CCB workflow process when development starts the work.
Create, publish and announce updated Deal Models & Pricing Calculators | §Selective previews by services (double precision), SCs (labor scheduling) | Add "Update Emerson Price Book" to the PDT Plan list
Customer feeback on AIMB running on AC 2.0 | §Teams also discussed various ways to improve estimates for word counts to work within the budget | Add a note at the top of the Download Center telling users how to request access to new versions
Deliver accurate documentation on time | §Teams are excited about using the Internal tool for localization. | Add Non-functional specification into new feature UC/ VTO , such as platform support, performance, compatibility. Test NRF earliy.
Desktop Launcher to consume tokens | §Teams were concerned about the accuracy of the translation for a couple of languages. | Add V14 to salesforce earlier to allow CS&T to update KBs earlier
DG: Customers with data privacy restrictions would be eager to deploy AIMB in a VPC | §Training session at end of release… | All product updates/changes need to be communcated better to all stakesholders so nothing is missed
DJV: Test in multiple customer cloud instances | §Triage emphasizing customer defects, SLO/SLA performance | Allocate time for and conduct indepth reviews of Use Cases, VTOS, and test cases as the work is being done.
Experience on custom code for platform specific things | · Achieved Code Freeze on October 14th instead of September 27th due to the following | Already discussed as a part of AAR for ENG Localization and actioned on
Fear, uncertainty and doubt on roadmap planning | · Achieved final Feature Freeze on Aug 29th instead of Aug 15th due to the following | APEM- The scope was not finalized as No Product Manager was assigned to the team which is the important factor to note for the delay on the CCB workflow.
Feedback from alpha to be incorporated as a part of the major/minor release | · Achieved final Scope Complete on Jul 19th instead of Jul 5th due to the following | Backlog grooming on a weekly basis to ensure that the backlog items are available for upcoming development, and explain the alignment of strategy.
Files prepared as a part of PI15 (after feature freeze) had documentation defects | · Achieved Release candidate on November 4th as planned with 1 CCB | Better view of the big picture (Dashboard) and also level of visibilty on what needs to happen when to accomplish PI goals, and release goals. (MVP before all other features)
Get customer feedback for improvements (installation, UX, etc) | · Backlog was significantly below the upper limit 121 at 70 (APEM) and 12 at 8 (AORA/ATOMS) at code freeze. | Can we have demo “scripts” followed in the end of release training available at time of turnover
Get final scope approved, no changes after approval | · Branching of code from one branch to another is one main cause of the defect backlog being high, key people from the team who worked on it left the team. | Change the package shares to align with the revenue order bundles (ENG, ENG for E&C, MSC, etc)
Keep defect limits below upper limit for v14 | · Resource were lost during the release [2 RnD and 1 QE]. | Check box of items for code reviews, implementation tasks – evergreen document…
List of sunset products finalized and approved | · CCB was created on 4/12 and until 7/5 the details of the CCB were not filled in as the scope of the CP was not finalized. | Continue the good work!
Log4j and DCOM interruptions | · CCB was created on 5/19 and until 6/22 the details of the CCB were not filled in. | Continue to have internal resources (VM) - WVD system with daily build - need access to PM earlier in the process.
Manage defect backlog within the threshold | 1.) Comparison of plan vs actuals on the scope of V14 release would help in future planning. | Continue to share new feature demos with Doc, since it has been very helpful.
Marketing launch week of GA with all new materials | 1.) V14 GDOT released as planned. | Could add "Notes" or "Change Log" field to our systems and sheets to record any changes so things aren't missed
Perform Automated testing for V14 | 10.) Customer Defects were low during the release. PM and CS&T customer engagement programs in recent release cycles have contributed towards process improvements and customer software adoption. | Deliver USBs at GA, get packaging approved and delivered to vendor earlier so there aren't any delays
Physical media (USBs) ready to ship alongside GA | 11.) PI flexibility (and iteration milestones) contributed to faster turnover time for defect resolution. | Dependency on the common components across products group, check with Sunil as a Platform Shift left initiative to enforce the artifact to happen. Tho to follow up with Sunil.
PI Planning | 12.) 1 or 2 EPs per Quarter were released for APC during the V14 development cycle. PM indicated this frequency seemed appropriate. | DG: Engage with customers at a higher level to understand their piorities in terms of platform deployments / IT resource allocation / Cloud strategy
Priortization of dependent features for ACCE | 2.) During the copy process from the HOU file drive, the file size (5GB) was showing as corrupted. | Documentation for new features – Online Help and Implementation Guides (PDF), clear communication on what it takes to drive doc tasks to completion, documentation versioning (perforce-like, checkout/edit) – process to condense cycle time
Provide a good alpha-beta experience to customers and gather usage details and feedback | 2.) Comparison of plan vs actuals on the scope of V14 release would help in future planning. | Escrow procedure should have been in place by the time we hit RC. Then we could have performed the escrow as part of the immediate follow-on work for RC. Request was sent to the teams after GA, where teams were fully into work on V15 and are expected to find a bunch of time for escrow. This is an unnecessary and foreseeable interruption in V15 work
Release all features marked for V14 release | 2.) Team recommended to continue with Iterative RUP approach for APC. | Have a dedicated meeting a few weeks prior to UAT to make sure the teams are aligned
Request for Enhancement CPs for ATOMS V14.0.1 CP for July’23 GA. Milestones (SC- 6/27, FF- 7/6, CF- 7/20, RC – 7/27, GA – 7/31). | 3.) The majority of Use Case turnovers were completed on time and fully tested by QE in a timely manner. | Have Tech team directly contact Customer representative to resolve technical issues rather than wait for meetings to be scheduled by Business counterparts.
RnD: Dependency of AEI (had competing business priorities) Reliant on AEI based solution initially, and changed direction to ENG solutions. But heavy implementation barrier with the solution developed by ENG and AEI database dependecy). | 3.) The majority of Use Case turnovers were completed on time and fully tested by QE in a timely manner. | Hire more QE resources to handle upcoming Inmation and Emerson OEM testing efforts.
Sales Enablement training held for SAMs, SCs and CS&T | 350 defects more than HYSYS came in after SC for AspenPlus (localization, integrarion defects) | How to handle customer submitted issues that have SLO/SLA but do not impact production applications
SC have better knowledge of Connect when it comes to configuring or deploying the same | 4.) PI15 focus was scheduled primarily for hardening intent, which provided both Development and QE with time to fully test the scope of the release. | Improve acceptance criteria and workflows associated with uses cases / turn overs (grooming), include configuration, customization
Scope was larger than the time available to implement and deliver it. | 4.) Resource allocation adjustments were made in PI14 for defect backlog fixing. Some non-MVP Use Cases were removed from scope for resource balancing. | Integrated use case testing – multigroup kickoff meeting (level setting, consistent understanding, workflow consensus/understanding, align expectations
Smooth V14 release | 5.) GDOT development team recommended continuing with Iterative RUP approach for GDOT. | Keep the same discipline when it comes to planning scope. We should also try to hire more QE resources to anticipate bigger backlog.
Staff churn | 5.) Starting from V12.1 and during the V14 release, Data Science team resources were lost, which impacted APC team in executing Use Cases. | Keep using the central repository for documentation, worked really well
Subcontactor Development and testing of Web IP.21 Administrator and Manager | 6.) Documentation gaps were found during the release. | Localization – visibility to what customers are using localized products – help prioritize/plan workload on test coverage
Testing upgrade of AIMB | 6.) Release Documentation and Installation Guide were completed on time, also getting the finance approvals on time. | Localization process (already had separate AAR)
The APC development team is to be able to meet all quality criteria milestones, with open defects below the backlog limit before the release. | 7.) Release Documentation and Installation Guide review time was less than optimal for meeting RC milestone. | Make the scedhule of RC and GA to two weeks (COMPLETED - Post V14, 2 weeks is allocated between RC and GA)
Thoughts on developing AC 2.0 for Azure and AWS | 8.) Early Beta was planned, allowing for incorporation of customer feedback for changes in the release. | Make use cases more granular where appropriate
Track Pre-Alpha activities and get closure on action items to start internal alpha activities | 9.) Extended Beta Program with Marathon improved customer communications and facilitated alignment for software usage before the release. | Many defects found while setting up VMs for demos = how can we do a better job of testing multiple configurations (not stand config as currently done by QE)
Update back office systems (SFDC, Oracle, etc) with new products for V14 | Academics bundle revision was not added to UPL and was not released with V14 | More complete unit testing prior to UAT to validate all changes are there
Update Emerson Price Book with new products | Achieved GA on November 14th as planned | Need a more accessible/central repository for training materials and recordings, planned earlier in the lifecycle to reduce the scramble at the end
Update eSupport site with new KBs and other updates | Action Log prepared with progress tracking documented with date stamp. Lot of useful info captured including the post-value activities. | Need a way to track which customer logged in, and the token usage log of how long did they test the product.
Update inventory in Oracle for the new media | AIMB is now more ready for Azure deployment than AWS deployment due to a number of factors, including the availability of services, the code base, and the loss of some key personnel. | Need to assess the tradeoff between Beta timeline vs. the readiness of all products (Decision needs to be made on time)
Update token tables & contracts | AIMB is platform agnostic because it uses an adapter to connect to different cloud storage providers, such as S3 on AWS and Azure Blob Storage on Azure.This means that AIMB can be used on any cloud platform, regardless of the underlying storage provider. This makes it a more flexible and scalable solution for building and deploying AI models. | Need to update and review Upgrade Package shares alongside the rest of the product updates
Update V14 LG/UPL with new products & licenses | All product documenation was posted for CS&T to start creating KBs early, created central repository for all documents to be posted as they were ready, worked really well | o Allocate resource for performance testing efforts with 1 feature (UC will be created for each PI) and last PI would be a hardening PI without MVP items planned
Upgrade Package Shares updated and approved with new products | APEM V14 CP1 for Sep’23 GA. Milestones (SC- 7/14 7/21, FF- 8/11, CF- 9/8, RC – 9/15, GA – 9/22) | o Big UC needs to be divided into different tasks or multiple UCs to enhance UC elaboration and delivery efficiency
V14 added to support site on GA | Approved products were added but needed to be removed late, created confusion on which products were approved and intended to be released | o Common custom and testing environment should be kept (three common machines at least and keep separate DB machines)
Validate all changes in UAT before pushing to PROD | ATOMS V14.0.1 CP for July’23 GA. Milestones (SC- 6/27, FF- 7/6, CF- 7/20, RC – 7/27, GA – 7/31). | o Default testing environment: remote SQL/Oracle Server
VM Access for PM / Demo kits ready up and running at about the launch date | Beta was delayed due to the readiness of Flare Analyzer (~3 weeks delay) | o Defect 817097 is brought in by resolving a customer issue which we updated the V14 UC incorrectly
We hoped for more QE to handle the ever growing backlog | Changes to spreadsheets/plans/systems were not always communicated, what changes wasn't recorded anywhere | o Descope option should be reviewed carefully when we encounter milestone delay issue
We would like to know if Chevron provided any feedback on the installation experience, UI, or UX. | CS&T needs to update all of the new KBs with new product version on GA morning, team has to spend several hours on GA day updating all the KBs with the correct version | o Expand Dev unit test coverage on all edge cases and devices/browsers
| Defect limits were way below the upper limit for Connect. (Upper Limit:50,Open defects 31) | o Increase QE resource allocation to 1.5 FTE in V15 release cycle for Petroleum MES
| Delay and Timeline of a CCB: | o MVP items should be identified in the early stage of release cycle
| DG: The persona at a customer who is eager to use AIMB is not the same as who is required to install it, and the latter is severely resource constrained | o Outline client/server protocol and communication in UC to enhance the communication between backend and frontend sides
| DJV: While several customers interested, only 1 got the internal support to follow through. | o Plan MVP turnover early and leave buffer for unexpected issues
| Documentation delivered on time. The team consistently assisted Seven and provided feedback in a timely fashion. | o Platform spec is missing for the client side and out-of-dated component should not be used
| During testing in UAT, there were things that seemed to not have been unit tested prior to UAT that needed to be updated on the fly, caused some delays in completing testing | o Record the defect change’s impact on the new UC and proceed through UC review/change procedure
| Easiness of controlling what is in the PI (rather than planning 18 months in advance) | o Review platform spec early and reach an agreement between R&D, PM and installation team
| Emerson Price Book published with no major issues | o SQL components should not in pre-installed in both R&D and QE testing environments
| Example file defects (mostly documentation) -- though the defects weren't code-related, it caused concerns for RR | o Suggestion: relational and multi-dimensional SQL component should be in separated merge module for ARF – need to review with Installation team to check if this will impact other products
| Example files delivered through knowledge Center increased the adoption | Open defect classification – strategic, fix in PI, do not delay between submit and fix (tend to forget details)
| Features turned over without pseudo localization | Pay more attention to performance testing. QE to formally summarize the performance testing results and all the related defects to both DEV and PV before Scope Complete, to allow more time on performance improvements. In v14.2, separated defects submitted and connected to specific developers, which did not get enough attention.
| Feedback from Senior management during CCB review meeting: | PDT Docs (Delivery Spec, NPD, etc) need to be finalized and approved no later thatn Feature Freeze (ideally SC if possible), any changes after approval should include discussion with all stakeholders and re-approval
| Found Ipad didn't support new feature during regression testing | Plan for SC Demo VMs to be ready with GA, cant do any training with customers until those are ready, sometimes takes several months before some demos are finished
| Good process to provision the environment and performance for customers | Pseudo localization done when features are turned over
| Hope did a good job of carrying forward from Amanda | Record all PDT meeting sessions, send out meeeting notes, and have more formal review and approval of scope with all required stakeholders
| Key messaging was not ready in time, created a bottleneck in publishing all the new materials | Review the content of this log when starting the next alpha activity. Also, review the post-alpha activities, and added them to Roadmap and other task trackers. Note: Pre-Alpha Tracker Worksheet has been added to this workbook for easy referencce.
| Late turnovers and schedule delays | RnD: When we realize that we are not making progress, establish the process for communicating and the right way to represent the status in the tool.
| –manage scope/deliverables (increase agility), quality control, defect control | SCs need to be cross trained and have better knowledge of configuring Connect.
| Marketing launch went well, updated and created a lot of new content | Separate plans (smartsheet) per category to better organize all the marketing activites, rolls up into a master report
| Marketing team used a smartsheet to help track all the required tasks that worked well, but it got very cumbersome with hundreds of lines of tasks, hard to find information/tasks | Setting up the VMs earlier, requests submitted by product team
| o CCB 814807 - Late fix for Defect 803389 (ARF) & Fix Request for Defect 817097 (AORA) after CF | Similar to code review, more document review needs to be conducted to ensure that there are no new documentation defects.
| o Scheduled testing is delayed and several defects are identified late which take time for both R&D and QE to handle | Start Elaboration earlier – late on requirements for starting PI construction
| o Team spent extra time to cover the auto-start edge case and fix related defects | Stricter GTM process, better defined timelines for key messaging content
| o We choose to fix as many important defects to provide V14 release with a good quality | Suggestion:
| o We inherit the delay from FF | Target to keep defects below max limit by end of each PI
| o We postponed the FF inheriting from SC delay to deal with 3 critical defects (Auto-start and complicated defect from performance testing) | Targeted alphas as and when the features are done. Take a look at contineous-alpha mode (isolate the product for point solution) Cross product workflow to be tackled in parallel (use dependencies to understand the readiness) Note: using tags in AHA doesn't provide the visibility in VSTS)for assessing alpha readiness.
| o CCB review should be completed first with Approvals, before the implementation and actual work getting started by the teams. This way the business value is fully understood by the leader’s team on the enhancement patch request. | Test with customer models
| Physical media was not ready at GA (delays with packaging) | Testing - Unit Testing, Automated Testing
| PI planning experience was way better as compared to previous releases. | The Product Manager should be the driver of the CCB from the business strategy side. Mention when CCB starts, PM should be the one to drive the CCB will help improve the process, as most of the time RnD Managers get assigned to drive.
| Pricing information for some of the more complex PLNs are not always clear in the NPD, having the PLN deck linked helps which we did better this time | The team is considering doing an alpha deployment with Azure, but may not be able to do one with AWS at this time. If a customer specifically requests AWS deployment, the team will need to assess the feasibility.
| Process of upgrading the VM with the V14 Access for PM and Demo kit preparation took longer. | The team should test and upgrade AIMB with the actual code before the next version is released. This will help to ensure that the upgrade process is smooth and that there are no unexpected problems.
| Product documentation was all posted on GA with no issues, customers able to submit cases | This is how Maestro currently does it, but we were unable to get access to this function. We have followed up with the relevant stakeholders, but have not yet received access. We believe that this is a simple and elegant way for customers to download the installer on their own, without requiring us to mail them or email them credentials. We are still working on this solution, and it is a priority on our roadmap.
| Products were descoped from the release, but was not communicated to all stakeholders until right before release | We need to add some markers in the code and the UI for them to hook on to be able to automate the test so there's some dev work.
| QE machine was borrowed for optiplant | We should plan better for v14.0.1 CP. Be very realistic of the resources and timeframe to deliver the same.
| RnD: AEI had competing business priorities for their staffing level. AEI tool was not up to what we were trying to do. | We slowed down towards the end because we had some internal questions to answer, but we would have liked to have a wider range of setups.
| Roadmap and Planning: Services project- nature of the Enhancements, taking testing plans into consideration. | Why was the in-rate so high, and what can be done to prevent it in future releases? Need root cause analysis and corrective actions.
| Sales Enable Training delivered week of GA, went well | Work with IS to get the process better defined (Bottleneck - VMs need to be prepared in advance for V14 access for PM team--- up and ready sooner)
SC Demo VMs were not ready alongside GA
Several customers were not included as part of the push upgrade and didn't see the new downloads at GA, weren't sure how to get access
Spreadsheet became messy and harder to follow with all the highlights/crossouts based on late changes, no change tracking to show what was changed/when
Sunset list was not finalized, created confusion right at the end around which products/licenses needed to be discontinued, some cleanup needed in the next release
Sustainabilty initiative increased the number of features to be delivered.
Technical training had some hiccups, became hard to track all the various trainings being delivered, gather recordings and meeting materials, etc. Making all of those accessible to CS&T/SCs is difficult
The AEI insights feature needed for ACCE, was broken down into two parts and only one was prioritized and was available for ACCE V14 delivery timeline. This has caused the descoping of ACCE
The amount of time we had to spend addressing these security issues seriously compromised our ability to get all the things accomplished that we had in our original plan. I cannot recall how many 100’s of person-hours were chewed up with these two issues, but it did have serious consequences on us.
The desktop launcher will then communicate with the license server to check out tokens before the application can be used. Chevron uses the desktop launcher to access tokens.
The roadmap was constantly unstable. One of our principals was engaged deeply in an acquisition. Our intentions were not always clear.
The team needs to test and upgrade AIMB before the next version is released. This has been done with a test application, but not with the actual code.
There were some misconfigurations that made connect look nonfunctional. These could have been avoided by understand configuring the product better.
Tighted the quality criteria for each of the milestones, timeline planned well between the milestones. E.g. pass rate for FF is 100% for new features, SC 70% (as compared to 50%)
Token table was published with a discontinued product still included that should have been removed
Translation errors
-Update center email notification says its posted but when go to the site, update center shows no patch posting.
Upgrade Packages were not finalized until right before the release, had to scramble late to confirm we had all the correct changes
Use cases, VTOs and Test cases did not cover off nominal paths. Significant reviews by QE and re-work by Infinitate are taking place now
User Ids are not unique to customers (pseudo user names were used)
V14 was not added to all the required areas in Salesforce/eSupport, caused some delays with posting documentation (i.e. Knowledge Base area was not updated)
-VPN from home to copy a file the chance of corruption is higher. If one is on AT Network the copy process is faster.
We could not automate our regression testing.
We seem to have stopped people from leaving, but it has been extremely difficult to replace those who have left, let alone the staff we had hoped for to work on the release.
We were short on QE resource and had to scope dev work appropriately.
We were very disciplined on planning the scope of work given the lack of QE resources. Our previous AAR really helped to get things under control.
WVD machine was provisioned, but needed sooner.